## GANTT
WARC PORTAL Plan
[9 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
|  |  |  | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
| ACTIVITY | Dependencies | ASSIGNED | START | DURATION | START | DURATION | COMPLETE | PERIODS
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74
| DATES | [7 empty] | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2
1 | User Stories |  | Kevin | 1 | 6 | 1 | 5 | 80%
2 | High Level Architecture Design |  | Cheng, Mate | 1 | 6 | 1 | 4 | 100%
3 | Project Management Plan V1 | 1,4 | Adriano | 1 | 6 | 1 | 4 | 100%
4 | Requirements Documentation | 1 | Mate, Kevin | 1 | 6 | 1 | 5 | 80%
5 | Storyboarding |  | Adriano | 1 | 6 | 1 | 4 | 100%
6 | UML Class Diagram | 1,2,5 | All | 22 | 5 |  |  | 0%
7 | UML Sequence Diagram | 1,2,5,6 | All | 22 | 5 |  |  | 0%
8 | UML Component Diagram | 1,2,5,6 | All | 22 | 5 |  |  | 0%
9 | Detailed System Architecture | 1,2,4,6 | All | 22 | 5 |  |  | 0%
10 | Requirements Documentation | 1,2,4 | All | 22 | 5 |  |  | 0%
11 | Design Document | 6,7,8,10 | All | 22 | 5 |  |  | 0%
12 | Finalize UI Design | 6,7,8,11 | All | 22 | 5 |  |  | 0%
13 | Project Management Plan V2 | 3 | Adriano | 28 | 1 |  |  | 0%
14 | MVP Documentation | 6-13 | All | 22 | 5 |  |  | 0%
15 | Test - US1 | 1,6,9,12 | Adriano | 14 | 8 |  |  | 0%
16 | Test - US2 | 1,6,9,12 | Adriano | 14 | 8 |  |  | 0%
17 | Test - US3 | 1,6,9,12 | Adriano | 14 | 8 |  |  | 0%
18 | Test - US4 | 1,6,9,12 | Cheng | 14 | 8 |  |  | 0%
19 | Test - US5 | 1,6,9,12 | Cheng | 14 | 8 |  |  | 0%
20 | Test - US6 | 1,6,9,12 | Cheng | 14 | 8 |  |  | 0%
21 | Test - US7 | 1,6,9,12 | Mate | 14 | 8 |  |  | 0%
22 | Test - US8 | 1,6,9,12 | Mate | 14 | 8 |  |  | 0%
23 | Test - US9 | 1,6,9,12 | Mate | 14 | 8 |  |  | 0%
24 | Test - US10 | 1,6,9,12 | Kevin | 14 | 8 |  |  | 0%
25 | Test - US11 | 1,6,9,12 | Kevin | 14 | 8 |  |  | 0%
26 | Test - US12 | 1,6,9,12 | Kevin | 14 | 8 |  |  | 0%
27 | Cybera Server Setup |  | Mate, Cheng | 7 | 4 | 1 | 4 | 100%
28 | HDFS Setup |  | Cheng + Adriano | 7 | 4 |  |  | 0%
29 | Front End App Skeleton | 27,28 | Kevin | 22 | 53 | 12 | 4 | 100%
30 | Backend App Skeleton | 27,28 | Cheng | 22 | 53 | 12 | 4 | 100%
31 | MySQL Install | 27,28 | Mate, Cheng | 22 | 53 | 12 | 4 | 100%
32 | File Selection functionality | 29,31 | All | 22 | 53 |  |  | 0%
33 | Image extraction | 29,30,31,32 | All | 22 | 53 |  |  | 0%
34 | Image packaging and downloading | 29,30,31,32 | All | 22 | 53 |  |  | 0%
35 | Duplicate text detection | 29,30,31,32 | All | 22 | 53 |  |  | 0%
36 | Keyword search | 29,30,31,32 | All | 22 | 53 |  |  | 0%
37 | Crawl Date extraction | 29,30,31,32 | All | 22 | 53 |  |  | 0%
38 | Graph visualization | 29,30,31,32 | All | 22 | 53 |  |  | 0%
39 | Term frequency (tf-idf) | 29,30,31,32 | All | 22 | 53 |  |  | 0%
40 | Term frequency graph | 29,30,31,32 | All | 22 | 53 |  |  | 0%
[14 empty] | S1 | [21 empty] | S2 | [17 empty] | S3 | [16 empty] | S4 | [10 empty] | S5

## Job Descriptions
Job Descriptions
Mate Verunica
Job Title | Description | Date Start | Date Due | Comments
Job Descriptions
Mate Verunica
Job Title | Description | Date Start | Date Due | Comments
Job Descriptions
Mate Verunica
Job Title | Description | Date Start | Date Due | Comments
Job Descriptions
Mate Verunica
Job Title | Description | Date Start | Date Due | Comments