## GANTT
WARC PORTAL Plan
[9 empty] | Period Highlight: |  |  |  |  | 0 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
|  |  |  | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
| ACTIVITY | Dependencies | ASSIGNED LEAD | START | DURATION | START | DURATION | COMPLETE | PERIODS
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73
| DATES | [7 empty] | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2
1 | User Stories |  | Kevin | 1 | 6 | 1 | 5 | 100%
2 | High Level Architecture Design |  | Cheng, Mate | 1 | 6 | 1 | 4 | 100%
3 | Project Management Plan V1 | 1,4 | Adriano | 1 | 6 | 1 | 4 | 100%
4 | Requirements Documentation | 1 | Mate, Kevin | 1 | 6 | 1 | 5 | 100%
5 | Storyboarding |  | Adriano | 1 | 6 | 1 | 4 | 100%
6 | UML Class Diagram | 1,2,5 | All | 22 | 5 | 24 | 4 | 100%
7 | UML Sequence Diagram | 1,2,5,6 | All | 22 | 5 | 24 | 4 | 100%
8 | UML Component Diagram | 1,2,5,6 | All | 22 | 5 | 24 | 4 | 100%
9 | Detailed System Architecture | 1,2,4,6 | All | 22 | 5 | 24 | 4 | 100%
10 | Requirements Documentation | 1,2,4 | All | 22 | 5 | 24 | 4 | 100%
11 | Design Document | 6,7,8,10 | All | 22 | 5 | 24 | 4 | 100%
12 | Finalize UI Design | 6,7,8,11 | All | 22 | 5 | 24 | 4 | 100%
13 | Project Management Plan V2 | 3 | Adriano | 28 | 1 | 27 | 1 | 100%
14 | MVP Documentation | 6-13 | All | 22 | 5 | 27 | 1 | 100%
15 | Cybera Server Setup | N/A | Mate, Cheng | 7 | 4 | 1 | 4 | 100%
16 | React Skeleton | N/A | Kevin | 22 | 10 | 12 | 4 | 100%
17 | Django Skeleton | N/A | Cheng | 22 | 10 | 12 | 4 | 100%
18 | MySQL Install | N/A | Mate / Cheng | 22 | 10 | 12 | 4 | 100%
19 | WARCBase Install | N/A | All | 22 | 10 | 12 | 20 | 100%
20 | Wayback Install | N/A | Adriano / Mate | 22 | 10 | 12 | 40 | 100%
21 | Hadoop Install | N/A | [5 empty] | 0%
22 | Sqoop Install | N/A | [5 empty] | 0%
23 | Image Processing Library Install | N/A | [5 empty] | 0%
24 | React + Django Link | 16,17 | Cheng & Kevin | 22 | 10 | 23 | 5 | 100%
25 | Running Test Web Service | 16,17,24 | Cheng | 29 | 3 | 23 | 9 | 100%
26 | Login Functionality | 16,17,18 | Kevin | 56 | 5 | 42 | 21 | 100%
27 | File mining functionality | 19,20 21,22 | Cheng, Adriano, Mate | 28 | 7 | 28 | 9 | 100%
28 | WARC file processing functionality | 19,20 21,22 | All | 28 | 7 | 28 | 9 | 100%
29 | Database link (Sqoop) | 19,20 21,22 | [5 empty] | 0%
30 | Image processing functionality | 27,28 29 | Cheng | 46 | 5 | 46 | 17 | 100%
31 | Image analysis functionality | 27,28 29 | Cheng | 46 | 5 | 46 | 17 | 100%
32 | Text analysis functionality | 27,28 29 | Cheng / Adriano | 40 | 6 | 46 | 17 | 100%
33 | TF-IDF functionality | 27,28 29 | Cheng | 51 | 5 | 60 | 3 | 100%
34 | Search engine | 27,28,32,33 29 | Kevin / Cheng | 40 | 6 | 40 | 6 | 100%
35 | Search filters | 27,28,32,33,34 29 | Kevin / Cheng | 46 | 5 | 50 | 10 | 100%
36 | Webpage display | 27,28 29 | Mate / Adriano | 40 | 6 | 40 | 6 | 100%
37 | Image search | 27,28,30,31 29 | Kevin | 51 | 5 | 42 | 20 | 100%
38 | Image display | 27,28 29 | Kevin | 51 | 5 | 42 | 21 | 100%
39 | Date extraction | 28,32 29 | Cheng | 46 | 5 | 38 | 2 | 100%
40 | Collection creation | 27 | Adriano / Mate | 56 | 5 | 37 | 26 | 100%
41 | Collection management | 27 | Adriano / Mate | 56 | 5 | 37 | 26 | 100%
42 | Search engine test suite | 34,35,37,38 | Adriano / Mate | 61 | 7 | 44 | 13 | 100%
43 | Collection engine test suite | 40,41 | Adriano / Mate | 61 | 7 | 61 | 13 | 100%
44 | Processing test suite | 19,20,27,28,30-33,39 | [5 empty] | 0%
45 | Database test suite | 18,29 | Cheng | 61 | 7 | 61 | 13 | 100%
46 | Admin documentation compilation | All | Adriano / Mate | 68 | 4 | 44 | 35 | 100%
47 | User documentation compilation | All | Adriano / Mate | 68 | 4 | 44 | 35 | 100%
48 | Screencast | All | Adriano | 72 | 1 | 72 | 2 | 100%
49 | Presentation and Delivery | All | All | 73 | 1 | 72 | 2 | 100%
[14 empty] | S1 | [20 empty] | S2 | [17 empty] | S3 | [16 empty] | S4 | [10 empty] | S5

## Job Descriptions
Job Descriptions
Mate Verunica
Job Title | Description | Date Start | Date Due | Comments
Job Descriptions
Mate Verunica
Job Title | Description | Date Start | Date Due | Comments
Job Descriptions
Mate Verunica
Job Title | Description | Date Start | Date Due | Comments
Job Descriptions
Mate Verunica
Job Title | Description | Date Start | Date Due | Comments